## Gantt Diagram
Gantt Diagram - DSE_FH_PRJ Project Tasks Planning

## Planning
Tasks | Start Date | End Date | Duration (days) | Engineer
Requirements Definition | 2019-07-26 | 2019-07-27 | 2 | HG | HG | FG
Architecture design | 2019-07-27 | 2019-07-30 | 4 | HG | Hector Guarneros | Francisco Govea
Architecture Validation | 2019-07-27 | 2019-07-30 | 4 | HG
Planing | 2019-07-27 | 2019-07-30 | 4 | HG
Configure e2 studio development environment | 2019-07-30 | 2019-07-30 | 1 | FG
Configure GUIX studio development environment | 2019-07-30 | 2019-07-30 | 1 | FG
Basic interface tests | 2019-07-30 | 2019-07-30 | 1 | FG
ADC reading | 2019-07-31 | 2019-07-31 | 1 | FG
ADC Implementation and Development | 2019-07-31 | 2019-07-31 | 1 | FG
ADC functionality tests | 2019-07-31 | 2019-07-31 | 1 | Team
ADC development documentation | 2019-07-31 | 2019-07-31 | 1 | FG
PWM reading | 2019-07-31 | 2019-07-31 | 1 | FG
PWM Implementation and Development | 2019-07-31 | 2019-07-31 | 1 | FG
PWM functionality tests | 2019-07-31 | 2019-07-31 | 1 | Team
PWM development documentation | 2019-07-31 | 2019-07-31 | 1 | FG
Encoder Reading | 2019-08-01 | 2019-08-01 | 1 | FG
Encoder Implementation and Development | 2019-08-01 | 2019-08-01 | 1 | FG
Encoder functionality tests | 2019-08-01 | 2019-08-01 | 1 | Team
Encoder development documentation | 2019-08-01 | 2019-08-01 | 1 | FG
Encoder / Motor functionality tests | 2019-08-01 | 2019-08-01 | 1 | FG
Encoder / Motor development documentation | 2019-08-01 | 2019-08-01 | 1 | FG
Validation of requirements with results obtained | 2019-08-02 | 2019-08-03 | 2 | HG
Documenting results | 2019-08-02 | 2019-08-05 | 3 | Team
Bug fixing | 2019-08-02 | 2019-08-05 | 3 | Team
PID control theory | 2019-08-03 | 2019-08-03 | 1 | FG
PID Implementation and Development | 2019-08-03 | 2019-08-03 | 1 | FG
PID functionality tests | 2019-08-03 | 2019-08-03 | 1 | Team
PID development documentation | 2019-08-03 | 2019-08-03 | 1 | FG
LCD driver reading | 2019-08-04 | 2019-08-04 | 1 | FG
LCD driver implementation and development | 2019-08-04 | 2019-08-04 | 1 | FG
LCD driver functionality tests | 2019-08-04 | 2019-08-04 | 1 | Team
LCD driver development documentation | 2019-08-04 | 2019-08-04 | 1 | FG
Define sprint 04 activities | 2019-08-04 | 2019-08-05 | 1 | HG

## Sprints
Tickets/Tasks/Issues | Epics | Sprints
DSE_FH_ScAg_001: Define-General-Requirements-from-Project-DSE #2 | DSE_FH_ScAg_000: Define-Requirements-of-the-DSE-Project #1 | Proj_DSE_FH_Sprint_001
DSE_FH_ScAg_002: Define-Specific-functional-requirements-and-inputs #3
DSE_FH_ScAg_003: Define-Operating-System-Control-algortihm-LCD-screen-and-Hardware-Requirements #4
DSE_FH_ScAg_005: Define-Activities-for-Sprint-003 | DSE_FH_ScAg_004: Define-Activities-plan-Architecture-design-and-Architecture-validation | Proj_DSE_FH_Sprint_002
DSE_FH_ScAg_006: Design-Architecture
DSE_FH_ScAg_007: Validate-Architecture
DSE_FH_SW_001: Configure-e2-studio-development-environment | DSE_FH_SW_000:Develop Software Architecture Modules | Proj_DSE_FH_Sprint_003
DSE_FH_SW_002: Configure GUIX studio development environment
DSE_FH_SW_003: Basic interface tests
DSE_FH_SW_004: ADC reading
DSE_FH_SW_005: ADC Implementation and Development
DSE_FH_SW_006: ADC functionality tests
DSE_FH_SW_007: ADC development documentation
DSE_FH_SW_008: PWM reading
DSE_FH_SW_009: PWM Implementation and Development
DSE_FH_SW_010: PWM functionality tests
DSE_FH_SW_011: PWM development documentation
DSE_FH_SW_012: Encoder Reading
DSE_FH_SW_013: Encoder Implementation and Development
DSE_FH_SW_014: Encoder functionality tests
DSE_FH_SW_015: Encoder development documentation
DSE_FH_SW_016: Encoder / Motor functionality tests
DSE_FH_SW_017: Encoder / Motor development documentation
DSE_FH_SW_018: Validation of requirements with results obtained
DSE_FH_SW_019: Documenting results
DSE_FH_SW_020: Bug fixing
DSE_FH_SW_021: PID control theory
DSE_FH_SW_022: PID Implementation and Development
DSE_FH_SW_023: PID functionality tests
DSE_FH_SW_024: PID development documentation
DSE_FH_SW_025: LCD driver reading
DSE_FH_SW_026: LCD driver implementation and development
DSE_FH_SW_027: LCD driver functionality tests
DSE_FH_SW_028: LCD driver development documentation
DSE_FH_SW_029: Define sprint 04 activities