## FMEA
ITEM | Department | ACTIVITY / RISK | Probability | Impact | Score | Action plan
1 | Hardware | Hardware fails due to some external damage | 3 | 5 | 15 | Ask the laboratory for information about device repairs or have to request devices for production
2 | Infrastructure | GIT server does not work | 3 | 5 | 15 | It is always necessary to have a local copy in case the server fails
3 | Management | No hay disponibilidad de licencias para desarrollar el proyecto | 1 | 1 | 1 | IT team must prevent this type of inconvenience, in the same way it is necessary to corroborate this information before starting any project
4 | Human Resources | Lack of expertise | 3 | 3 | 9 | It is essential to ask the HR department the required training for the software team
5 | Hardware | Device malfunction. | 3 | 5 | 15 | When software personal receive the new equipment it is necessary to perform functionality tests before starting the validation tests
6 | ITV | Incorrect validation | 1 | 5 | 5 | It is intended to have constant Peer-reviews between the Sw, system and ITV teams, where the requirements must be analyzed and ensure that everyone correctly understands each of the requirements. The ITV team must also make Peer-Reviews of their test cases before running a round of tests oficial
7 | Management | Availability or access to equipment | 3 | 3 | 9 | If there is not enough HW, it is necessary that the members of the team organize themselves to generate a schedule in which each engineer will make their test round
8 | Laboratory | Badly calibrated measuring equipment | 1 | 3 | 3 | Establish dates for calibration of the measuring equipment with the Laboratory department
9 | Software | Ilegibilidad del código | 3 | 5 | 15 | Code ineligibility
10 | Systems | Ambiguous requirements | 3 | 5 | 15 | It is intended to have constant Peer - Reviews among the Sw, system and ITV teams, where the requirements must be analyzed and ensure that there is no ambiguity in each of the requirements.
11 | Build Management | Do not do integration tests | 3 | 3 | 9 | El equipo de Build Management debe de presentar la documentación necesaria en cada liberación que realice.
12 | Software & Build Management | Integration procedure ignored | 3 | 3 | 9 | Build Management team must present the necessary documentation showing the release validation.
13 | ALL | Lack of documentation | 3 | 3 | 9 | All teams must present the necessary documentation in each of their deliveries, all the documentation must show traceability with the development of the code
14 | ALL | Brain drain | 5 | 5 | 25 | All teams must present the necessary documentation in each of their deliveries, all the documentation must show traceability with the development of the code, this as a contingency plan in case of brain drain. Similarly, it is expected to take more appropriate measures.
15 | Software | Wrong design | 5 | 5 | 25 | It is intended to have constant Peer - Reviews among the Sw, system and ITV teams, where the requirements must be analyzed and ensure that there is no ambiguity in each of the requirements. Based on the expertis the design is expected to be as accurate as expected by our client